## Sheet1
Major Criteria/Minor Criteria | Status
Non-Pawn, non-King pieces concealed at game start. | Done
Concealed pieces can move 1-2 spaces, any unobstructed direction. | Done
Concealed pieces can be arranged by players at game start. | In-Progress
Pieces can be arranged by the player at the start of the game. | Done
A GUI is provided to allow human players to arrange their pieces. | Done
Pieces are randomly arranged by the computer at the start of the game. | In-Progress
Concealed pieces can capture other pieces and put King in check. | In-Progress
Concealed pieces can capture other pieces. | Done
Concealed pieces can put the King in check. | In-Progress
Concealed pieces can be revealed as their intended piece. | Done
One queen can be revealed | Done
Two knights can be revealed | Done
Two bishops can be revealed | Done
Two rooks can be revealed | Done
The positions of the revealed pieces follows the desired arrangement. | Done
Pieces are revealed correctly even when the Concealed piece is moved. | Done
Castling move has been made unavailable due to rule changes. | In-Progress
Revealing a piece counts as a turn. | Done
Artificial Intelligence has memory for the location of concealed pieces. | In-Progress
Artificial Intelligence can remember which concealed piece is which. | In-Progress
Artificial Intelligence can forget which concealed piece is which. | In-Progress
Artificial Intelligence uses concealed pieces properly | In-Progress
Artificial Intelligence moves Concealed pieces properly. | In-Progress
Artificial Intelligence decides to reveal Concealed pieces properly. | In-Progress
Concealed pieces are represented on the chess board. | In-Progress
White concealed pieces are represented with a unique sprite. | Done
Black concealed pieces are represented with a unique sprite. | Done
Concealed sprites are replaced with the corresponding piece sprite when revealed. | Done
Concealed sprite movement maps are represented properly on the chess board. | Done
Captured concealed sprites are properly represented in the list of captured pieces. | In-Progress